## Sheet1
Gantt Chart – Language Institute Project
Task | Assigned To | Start | End | Mar 30 | Mar 31 | Apr 01 | Apr 02 | Apr 03 | Apr 04 | Apr 05 | Apr 06 | Apr 07 | Apr 08 | Apr 09 | Apr 10 | Apr 11 | Apr 12 | Apr 13 | Apr 14 | Apr 15 | Apr 16 | Apr 17 | Apr 18
Project Planning | All Members | 2026-04-03 | 2026-04-04 | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
UI/UX Design (Home Page) | Fawz Alazmi | 2026-04-04 | 2026-04-06
UI/UX Design (Courses Page) | Joud Khalid Alharbi | 2026-04-06 | 2026-04-09 | bar: Apr 03 F to Apr 04 S
UI/UX Design (Other Pages) | Haya Alqahtani | 2026-04-06 | 2026-04-10 | bar: Apr 04 S to Apr 06 M
GitHub Setup & README | Amal Alsawidan | 2026-04-08 | 2026-04-11 | bar: Apr 06 M to Apr 09 T
Review & Improvements | All Members | 2026-04-11 | 2026-04-13 | bar: Apr 06 M to Apr 10 F
Final Submission | All Members | 2026-04-13 | 2026-04-15 | bar: Apr 08 W to Apr 11 S